PLANNING PERFORMANCE AGREEMENT

Parties

This Agreement is made on	[DATE] 	between the following parties:

(1) London Borough of Hillingdon, Civic Centre, High Street, Uxbridge, Middlesex, UB8 1UW (“LBH”); and

(2)  [  FULL NAME AND ADDRESS ] (“the Developer”)

- Recitals

  - LBH is the local planning authority for developments falling within its local government area boundary.

  - The Developer intends to submit a Planning Application to LBH in respect of the Development specified in Schedule 1.

  - The Developer and LBH recognise that the Development will give rise to a wide range of planning issues and, accordingly, they acknowledge that in order to properly assess those planning issues the Planning Application may not be capable of being determined within the 13 (16) week statutory period. Nevertheless both parties wish to ensure that the application(s) is/are considered in a timely manner and as expeditiously as is practicable.

  - In these circumstances, the Developer and the LBH agree to enter into this Planning Performance Agreement (as specified in Schedule 6) for the following purposes:

  - to agree requirements and timescales in the form of Performance Standards (Schedules 3 and 4) and a Project Programme (Schedule 5) for the consideration and determination of the Planning Application;

  - to establish appropriate measures for monitoring compliance with the respective parties’ obligations under this agreement; and

  - to establish regular review mechanisms in respect of the Project Programme.

  - This Planning Performance Agreement is made pursuant to Section 111 of the Local Government Act 1972, Section 2 of the Local Government Act 2000 and Section 93 of the Local Government Act 2003.

  - Nothing in this agreement shall restrict or inhibit LBH from properly exercising its role as the local planning authority. It will not prejudice the outcome of the planning (and related) application(s) or the impartiality of the LBH.

  - Nothing in this agreement shall restrict or inhibit the Developer from exercising their right of appeal under Section 78 of the Town and Country Planning Act 1990.

- Term

  - This Agreement will apply from the Commencement Date (being the date the Planning Application is submitted to LBH and is registered on the statutory register as a valid planning application) and (subject to earlier determination as hereinafter provided) shall be effective for the period up to the determination of the application, as specified in Schedule 6 (or such extension of this Term in accordance with the terms of this Agreement).

  - The Term shall be subject to review as may be agreed between the Parties and set out below under section 7.

  - Should the Developer submit an appeal under Section 78 of the Town and Country planning Act 1990 in relation to the Planning Application (for whatever reason) or should the Planning Application be called in by the Secretary of State, this Agreement shall automatically terminate.

- Joint Working and Duty to Act Reasonably

  - All Parties shall act with the utmost fairness and good faith towards each other, acting honestly and with integrity, being reasonable and rational in respect of all matters relating to the handling of the Planning Application(s) and to work jointly with each other in complying with their respective obligations under this Agreement.

  - The parties will work proactively together to resolve issues in a manner which avoids, to the extent possible, the need for pre-commencement conditions.

- Developer’s Obligations

  - The Developer agrees to use its reasonable endeavours to:

- submit a planning application to LBH for the Development set out in Schedule 1 by the Commencement Date set out in Schedule 6.

- submit the documents set out in Schedule 2 with the Planning Application when it is submitted to LBH.

- comply with the Performance Standards set out in Schedule 3.

- comply with and facilitate the compliance by LBH with the Indicative Project Programme set out in Schedule 5.

- perform the obligations set out in the Planning Performance Agreement at Schedule 6.

- Commence work on the Section 106 agreement(s) within 4 weeks of validation of the application(s) unless both parties agree otherwise.

  - In the event that the processing of this Planning Application(s) requires the LBH to obtain advice from specialist external consultants, advice which would incur costs outside the scope of those contained in paragraph 6.1, LBH may request in writing agreement to additional fees to meet these costs.  Should such agreement not be received within 10 working days of the request, any obligation on LBH to accord with the timetable in Schedule 6 shall be removed and an alternative timetable must be agreed in writing.

- LBH’s Obligations

  - Without prejudice to its other obligations as local planning authority, LBH agrees to use its reasonable endeavours to:

- designate a planning officer who alone or as part of a team shall be responsible for overseeing or carrying out the functions in accordance with this agreement

- comply with the Performance Standards set out in Schedule 4.

- comply with and facilitate the compliance by the Developer with the Indicative Project Programme set out in Schedule 5.

- perform the obligations set out in the Planning Performance Agreement at Schedule 6.

- Fees

  - In consideration of this agreement the Developer agrees to pay LBH £XXXXX (+ VAT) to assist LBH in providing the level of service required to meet its obligations under this Planning Performance Agreement. This fee is in addition to the application fees payable under the Town and Country Planning (fees for Applications and Deemed Application) (Amendment) (England) Regulations 2008.

- Amendment/Review of agreement

  - Amendment to the agreement and revision of timescales shall be subject to review as may be agreed between the parties.

SCHEDULE 1

The Development

Address of the application site:

[INSERT FULL ADDRESS]

Description of the Development:

[INSERT DESCRIPTION OF DEVELOPMENT]

SCHEDULE 2

The Application Documents

The parties to this Agreement agree that the Planning Application shall be accompanied by the following documents:

The statutory national list of planning application requirements:

- Completed form

- Site location plan

- Other plans/information necessary to properly describe the development

- Ownership certificate & notice

- Agricultural holdings certificate

- Design and Access statement

- Appropriate fee

- CIL Additional Questions Form

The local list of planning application requirements*:

[DELETE AS NECESSARY]

- Aviation Safeguarding Report

- Affordable housing Statement

- Financial Viability Assessment (subject to FASTTRACK)

- Daylight/Sunlight Assessment

- Environmental Statement

- Noise Impact Assessment

- Air Quality Assessment

- Flood risk assessment

- Fire Strategy/Tall Building Fire Statement

- Land Contamination Assessment

- Landscaping details inc. Urban Greening Factor

- Open Space Assessment

- Photographs and Photomontages

- Planning obligations/Draft Heads of Terms (Including Applicants Solicitors details)

- Planning Statement

- Transport Assessment

- Travel Plan (draft)

- Tree Survey/Arboricultural Report

- Amenity/Playspace Assessment

- Energy Efficiency Statement

- Overheating Strategy

- Lifetimes Homes Statement

- Microclimate Assessment

- Regeneration Statement

- Circular Economy Statement

- Refuse Strategy

- Secure by Design Statement

- TV & Radio-reception Impact Assessment

- Views Assessment

- Accessibility Statement

- Statement of Community Involvement

- Whole Life-Cycle Carbon Assessments

* This list could be subject to change in the event of new legislative/policies that are adopted prior to submission of an application.

SCHEDULE 3

The Developer’s Performance Standards

The Developer agrees to use its reasonable endeavours to achieve the following performance standards at all times:

- To carry out such public consultation as may be reasonably requested by LBH as soon as reasonably practicable.

- To wherever possible address any concerns raised by any consultee prior to the submission of the planning application to LBH.

- To include the written consultation responses received from consultees with the Planning Application.

- To provide LBH with such additional information as may be requested within 5 working days of such written request from LBH (or such other time period as may be agreed) in order to enable LBH to discharge its responsibilities.

- To provide to LBH at least 10 working days prior to any meeting all substantive and relevant documents which are relevant to that meeting and which relate to any relevant action points or agenda item identified.

- To provide to LBH within 10 working days of any meeting the minutes or action points arising from that meeting.

- To act in a reasonable, rational and professional manner in all dealings with LBH.

- To genuinely seek to make alterations to proposals in order to address concerns raised by the Council.

SCHEDULE 4

LBH’s Performance Standards

In addition to its statutory obligations, LBH agrees to use its reasonable endeavours to achieve the following performance standards at all times:

- Respond substantively to all faxes, emails, letters and telephone calls within 10 working days of receipt. Where circumstances beyond the reasonable control of LBH prevent its compliance with this Performance Standard, LBH shall in each case notify the Developer of such circumstances.

- Notify the Developer no later than 5 working days prior to any meeting of the Major Applications Planning Committee at which any report or matter relevant to the Development will be discussed and or considered and to provide the Developer with a copy of any report at that time.

- To provide to the Developer within 10 working days, comments relating to meeting minutes or action points issued by the Developer following a meeting between both parties.

SCHEDULE 5

The Indicative Project Programme

The parties to this Agreement have agreed to use their reasonable endeavours to ensure that the Planning Application is progressed in accordance with the Planning Performance Agreement (unless subsequently varied) and the following Project Programme indicates the stages and timescales necessary in order to achieve that. For the avoidance of doubt this Project Programme does not form part of the Planning Performance Agreement.

| 1. Pre-application stage |  |
| --- | --- |
| Pre-application discussions and consultation | INSERT DATE |

| 2. Project Team |
| --- |
| Name | Position & Role | Contact Details |
| CASE OFFICER | INSERT | EMAIL ADDRESS AND DIRECT DIAL |
| LINE MANAGER | INSERT | EMAIL ADDRESS AND DIRECT DIAL |

3. Project plan

| Action / Task | Responsibility | Timetable / Target Date |
| --- | --- | --- |
| Submission of Application | Applicant | As per Schedule 6 |
| Validation Check of Planning Application | Case Officer | 5 working days of submission |
| Issue statutory consultation and notification letters within 5 working days of validation (Can only be done once the application has been Validated) | Case Officer | Within 5 working days of the Validation |
| Provide full instructions to the Council's Legal team | Case Officer | Within 4 working weeks of Validation |
| Issue Consultee Comments received to Applicant | Case Officer | Within 5 working weeks of Validation |
| Arrange a review meeting to discuss responses received in relation to the consultation (and any other issues which have arisen during the assessment process) | Case Officer | Within 6 working weeks of Validation |
| Revisions to the Proposed Application: The applicant to submit a single set of revisions, where possible | Applicant | Within 5 working days |
| Revisions to the Proposed Application: The Council to issue comments received from consultees within 3 days of receipt | Case Officer | 3 working days from receipt |
| Provide full list of final drawing and documents, with 1 hard copy set and 1 CD. | Applicant | 3 working weeks before committee date |

SCHEDULE 6

The Planning Performance Agreement

The parties to this Agreement shall use their reasonable endeavours to perform the following obligations that constitute this Planning Performance Agreement.

| A | The Commencement Date: the date the Planning Application is to be submitted to LBH by the Developer | INSERT |
| --- | --- | --- |
| B | The Determination Date: the date the Planning Application is to be reported to committee or considered under delegated powers by LBH | INSERT Eg. Feb/March 2021 |
| C | The Referral Date: the date the Planning Application is referred to the London Mayor (if required by Statutory Instrument) by LBH | Within 5 working days of finalisation of Legal Agreement |
| D | The Decision Date: the date the planning decision is issued by LBH | Not later than 4 weeks following receipt by LBH of any direction made by the committee (subject to finalisation of any Legal Agreement and GLA referral) |

Signatures

Signed by the parties or their duly authorised representatives

LB Hillingdon

| Noel Kelly for and on behalf of LB Hillingdon |  |
| --- | --- |
| Date |  |

The Developer

| [NAME] for and on behalf of The Developer |  |
| --- | --- |
| Date |  |